## Sheet1
Actor Type | Description | Weighting Factor | Number | Result
Simple | External System with well-defined API | 1 | 2 | 2
Average | External system using a protocol based interface as TCP/IP | 2 | 0 | 0
Complex | Human interacts through Graphic User Interface (GUI) or Web Page | 3 | 8 | 24
Unadjusted Actor Weight Total (UAW) |  |  |  | 26
Use Case Type | Description | Weighting Factor | Number | Result
Simple | 1 – 3 transactions | 5 | 2 | 10
Average | 4 – 7 transactions | 10 | 1 | 10
Complex | > 7 transactions | 15 | 2 | 30
Unadjusted Use Case Weight Total (UUCW) |  |  |  | 50
UUCP (UAW + UUW) |  |  |  | 76
Factor Number | Description | Weight | Assigned Value | UCP Weighted Value
(0–5)
T1 | Distributed Systems | 2 | 5 | 10
T2 | Response time or throughput performance objectives | 1 | 3 | 3
T3 | End-user online efficiency | 1 | 4 | 4
T4 | Complex internal proccesing | 1 | 3 | 3
T5 | Reusability of code | 1 | 4 | 4
T6 | Easy to install | 0.5 | 5 | 2.5
T7 | Ease of use | 0.5 | 5 | 2.5
T8 | Portability | 2 | 5 | 10
T9 | Ease of change | 1 | 5 | 5
T10 | Concurrency | 1 | 4 | 4
T11 | Special security objectives included | 1 | 2 | 2
T12 | Direct access for third parties | 1 | 3 | 3
T13 | Special user training required | 1 | 1 | 1
Nilai Tehnical Factor (TF) |  |  |  | 54
TCF = 0.6 + (0.01 * TF) |  |  |  | 1.14
Factor Number | Description | Weight | Assigned Value (0–5) | UCP Weighted Value
E1 | Familiarity with system development process being used | 1.5 | 3 | 4.5
E2 | Application experience | 0.5 | 4 | 2
E3 | Object oriented experience | 1 | 4 | 4
E4 | Lead analyst capability | 0.5 | 5 | 2.5
E5 | Motivation | 1 | 5 | 5
E6 | Requirements stability | 2 | 3 | 6
E7 | Part time staff | -1 | 0 | 0
E8 | Difficulty of programming language | -1 | 2 | -2
Nilai Environmental Factor (EF) |  |  |  | 22
ECF = 1.4 + (-0.03 * EF) |  |  |  | 0.74
UCP = UUCP * TCF * ECF |  |  |  | 64.1136
Effort = UCP * Effort Rate |  |  |  | 40242.82
Estimated duration = 300 Hours / 2 weeks
Activities | Pay rate per hours (rupiah)
Needs analysis (Requirement) | 40462
Specification | 40462
Design | 28902
Implementation | 28902
Acceptance & installation | 28902
Project management | 86705
Configuration management | 86705
Documentation | 28902
Training & technical support | 28902
Integrated testing | 28902
Quality assurance | 46243
Evaluation & testing | 28902
Phase/Activities | Prosentase Effort Distribution | Effort Distribution | Cost Estimation (rupiah)
Software Phase Development | 72.6% | 217.8
Needs analysis (Requirement) | 12% | 36 | 1456632
Specification | 10% | 30 | 1213860
Design | 16% | 48 | 1387296
Implementation | 16% | 48 | 1387296
Acceptance & installation | 18.6% | 55.8 | 1612731.6
Ongoing life-cycle activity | 17.5% | 52.5
Project management | 8% | 24 | 2080920
Configuration management | 6.5% | 19.5 | 1690747.5
Documentation | 1.5% | 4.5 | 130059
Training & technical support | 1.5% | 4.5 | 130059
Quality and testing phases | 9.9% | 29.7
Integrated testing | 2% | 6 | 173412
Quality assurance | 2.4% | 7.2 | 332949.6
Evaluation & testing | 5.5% | 16.5 | 476883
Total | 100% | 300 | 12072845.7